## Acceptance
MWU Acceptance Checklist
Complete per milestone; attach evidence and record open items
Acceptance ID | Milestone | Layer | Acceptance criterion | Required evidence | Actual result | Status | Notes / open item
ACC-L1A-01 | Layer 1 | L1a | WAV preflight and canonical clock succeed. | Run report and manifest | Synthetic preflight and manifest tests executed; QA2 pending. | Not Ready
ACC-L1A-02 | Layer 1 | L1a | Every generated acoustic candidate is exposed; the system does not infer participant or incidental identity. | WebUI screenshot and run configuration | Candidate exposure and identity-boundary UI tested; QA2 pending. | Not Ready
ACC-L1A-03 | Layer 1 | L1a | Researcher can listen, include/exclude/merge and map candidates to S1-SN. | Candidate review record | Reviewer ID, listening, decisions and S1-SN mapping tested; QA2 pending. | Not Ready
ACC-L1A-04 | Layer 1 | L1a | Confirmed mapping produces RTTM/CSV, speaker TextGrid and muted mirrors. | Phase I artifact package | Artifacts, checksums and stale-handoff blocking tested; QA2 pending. | Not Ready
ACC-L1B-01 | Layer 1 | L1b | P025 and P035 run independently on the canonical timeline. | Method record and draft artifacts |  | Partial
ACC-L1B-02 | Layer 1 | L1b | Dynamic N+3 schema passes for the accepted participant count. | Schema validation report |  | Not Ready
ACC-L1B-03 | Layer 1 | L1b | Nine labels, R1-R5 and Path B missing-overlap semantics are preserved. | Validation and transition evidence |  | Partial
ACC-L1B-04 | Layer 1 | L1b | Reviewed TextGrids can be uploaded and final durations cite reviewed inputs. | Finalization report |  | Partial
ACC-L2-01 | Layer 2 | L2 | Required research definitions and Gold examples are recorded. | Definition readiness record |  | Not Ready
ACC-L2-02 | Layer 2 | L2 | RAW/TIDY, AS-unit, lexical/MWU, pause and rate outputs match approved examples. | Layer 2 validation package |  | Not Ready
ACC-L3-01 | Layer 3 | L3 | Final matrix and workbook match the signed schema/codebook. | Matrix reconciliation report |  | Not Ready
ACC-L3-02 | Layer 3 | L3 | WebUI exposes accepted outputs and archive-ready downloads. | Browser QA and release package |  | Not Ready
ACC-HND-01 | Handover | All | Source, scripts, configuration templates and guides are delivered. | Handover manifest |  | Not Ready
ACC-HND-02 | Handover | All | Client server passes build, health, representative job and download checks. | Operational verification |  | Not Ready

## Open Items
Open items register
Record material non-conformities and agreed disposition
Issue ID | Acceptance ID | Description | Type | Severity | Owner | Target date | Status
|  |  | Bug / Question / Enhancement |  |  |  | Open

## Sign-off
Release sign-off
Record the accepted release and any surviving open items
Field | Value | Field 2 | Value 2
Project | MWU research-processing system
Release identifier
Accepted milestone
Client representative |  | Date
Provider representative |  | Date
Open items reference | See Open Items sheet
Acceptance decision